| Task Order: | G14PD01045 – San Diego, CA 2014 Ortho and LiDAR |
| --- | --- |
| Reporting period: | April 1 – April 30, 2015 |
| Report Date: | May 7, 2015 |

Project Summary:

Provide high resolution ortho imagery and QL1/QL2 LiDAR for San Diego County and a small portion of Tijuana, Mexico, totaling approximately 1505 square miles.  Provide imagery for remainder of County.

Summary of work completed during reporting period:

- Continued ortho production

- Finished initial LiDAR calibration processing of all missions, and began classification

- Delivered Lidar Pilot Data

Outstanding issues and concerns:

- None at this time

Schedule:

The overall project is 79% complete

| Task & Sub-Task | Percent Complete | Due | Finish |
| --- | --- | --- | --- |
| Lot 1 - Kick Off Meeting [1%] | 100% | 10/10/2014 | 10/06/2014 |
| Lot 2 - Imagery Acquisition [24%] | 100% | 02/27/2015 | 2/24/2015 |
| Lot 3 - LiDAR Acquisition [24%] | 100% | 02/27/2015 | 2/24/2015 |
| Lot 4 - Ground Control [8%] | 100% | 2/01/2015 | 12/2/2014 |
| Lot 5- Digital Stereo Pairs [2%] | 100% | 3/30/2015 | 2/25/2015 |
| Lot 6- Pilot LiDAR Pilot [4%] | 95% | 4/15/2015 | 4/15/2015 |
| Lot 7- 10cm (4") Digital Orthophotography [8%] | 25% | 6/15/2015 |  |
| Lot 8 - 30cm (1') Digital Orthophotography [4%] | 85% | 7/15/2015 |  |
| Lot 9 - LiDAR Data [13%] | 80% | 6/15/2015 |  |
| Lot 10 - Final Data Set Copies [2%] |  | 8/15/2015 |  |
| USGS Final Acceptance [10%] |  | 8/30/2015 |  |

Activities Planned Next Month:

- Review USGS Lidar Pilot Report when provided

- Commence Lidar production for final deliverables

- Continue ortho production