| Task Order: | G14PD01045 – San Diego, CA 2014 Ortho and LiDAR |
| --- | --- |
| Reporting period: | May 1 – May 31, 2015 |
| Report Date: | June 8, 2015 |

Project Summary:

A portion of San Diego County and a small portion of Tijuana, MX (together totaling approximately 1,505 square miles), was collected at an image resolution of 30cm. Additionally, a portion of San Diego County (approximately 1135 square miles) and Camp Pendleton (approximately 253 square miles) were collected at a ground resolution of 10cm along with QL2 LiDAR at a resolution of 2 points per square meter. An additional area of 2,906 square miles of high resolution 30cm ortho imagery in eastern San Diego County was added as a modification to the original task order, for a total of 4,411 square miles. An additional area of 40 square miles of QL1 LiDAR acquisition in portions of San Diego County was added as a modification to the original task order. An additional area of 11 square miles of QL2LiDAR acquisition over a portion of Tijuana, Mexico was added as a modification tothe original task order.

Summary of work completed during reporting period:

- Completed initial processing of the 30cm orthophotography

- Continued the initial processing of the 10cm orthophotography

- Reviewed the LiDAR Pilot QC report, and implemented procedures to correct the issues that were noted in the report

- Completed the initial processing of the QL1/QL2 LiDAR

Outstanding issues and concerns:

- None at this time

Schedule:

The overall project is 86% complete

| Task & Sub-Task | Percent Complete | Due | Finish |
| --- | --- | --- | --- |
| Lot 1 - Kick Off Meeting [1%] | 100% | 10/10/2014 | 10/06/2014 |
| Lot 2 - Imagery Acquisition [24%] | 100% | 02/27/2015 | 2/24/2015 |
| Lot 3 - LiDAR Acquisition [24%] | 100% | 02/27/2015 | 2/24/2015 |
| Lot 4 - Ground Control [8%] | 100% | 2/01/2015 | 12/2/2014 |
| Lot 5- Digital Stereo Pairs [2%] | 100% | 3/30/2015 | 2/25/2015 |
| Lot 6- Pilot LiDAR Pilot [4%] | 100% | 4/15/2015 | 4/15/2015 |
| Lot 7- 10cm (4") Digital Orthophotography [8%] | 90% | 6/15/2015 |  |
| Lot 8 - 30cm (1') Digital Orthophotography [4%] | 95% | 7/15/2015 |  |
| Lot 9 - LiDAR Data [13%] | 95% | 6/15/2015 |  |
| Lot 10 - Final Data Set Copies [2%] |  | 8/15/2015 |  |
| USGS Final Acceptance [10%] |  | 8/30/2015 |  |

Activities Planned Next Month:

- Complete Final QC of 10cm Orthophotography and make delivery of Lot 7

- Complete Final QC of 30cm Orthophotography and make delivery of Lot 8

- Complete Final QC of LiDAR and make delivery of Lot 9